Appendix B:

Resources

This appendix provides resources you can use to expand your understanding of project management, and updates will be added as needed. You will find a listing of the template files (and be able to download them all in one compressed file), three detailed case studies, information on project management simulation software and MindView Business software, and project management certification information. Feel free contact the authors at schwalbe@augsburg.edu with any questions or suggestions.

Note: This appendix is for the text book Healthcare Project Management by Kathy Schwalbe and Dan Furlong.  www.healthcarepm.com.

# Introduction

This appendix summarizes resources you can use to expand your understanding of project management. It describes information provided on the companion Web site, summarizes information about template files, provides detailed case studies, discusses the option to use project management simulation software, briefly describes MindView Business software, and provides information and resources on project management certifications.

# Companion Web Sites

## For Students (www.healthcarepm.com)

The student companion Web site for this text is not password-protected. Anyone can access it. In addition to this appendix, the site includes the following:

- Important links and documents mentioned in the text

- Interactive, multiple-choice quizzes for each chapter where you can test your understanding of key concepts

- Jeopardy games for each chapter created in PowerPoint, another method for testing your understanding of materials

- Template files, as described in the following section

- Microsoft Project information, including necessary data files for performing steps in Appendix A

- Links to additional resources related to project management

## For Instructors

The instructor companion Web site for this text is password-protected. Contact the author at schwalbe@augsburg.edu to verify that you are an instructor using this text to gain access. In addition to the information on the student site, the instructor site includes the following:

- Lecture slides for each chapter, created in PowerPoint. Note: These slides are copyrighted and must remain on a secure site. Instructors can copy them onto their own school’s secure network and make changes as desired as long as the copyright information remains on each slide.

- An instructor manual and solutions manual for the text

- Several test banks

- Teaching ideas, including information on using real projects in classes and using other cases, such as those from Harvard Business Review

- Ideas and inputs from other instructors

# Template Files

As mentioned throughout this text, using templates can help you prepare various project management documents, spreadsheets, charts, and other files. Figure B-1 lists the template name, the chapter where it is used in the text, and the application software used to create it. Be careful to enter information into the templates carefully, and feel free to modify the templates to meet your particular project needs. You can download the files in one compressed file (hcpm templates) from the companion Web site.

| Template name | Chapter | Application software |
| --- | --- | --- |
| Payback period chart | 2 | Excel |
| Weighted scoring model | 2 | Excel |
| Stakeholder register | 3 | Word |
| Stakeholder management strategy | 3 | Word |
| Business case | 3 | Word |
| Business case financials | 3 | Excel |
| Charter | 3 | Word |
| Kick-off meeting agenda | 3 | Word |
| Team contract | 4 | Word |
| Project management plan | 4 | Word |
| Project organizational chart | 4 | Word |
| Requirements management plan | 4 | Word |
| Requirements traceability matrix | 4 | Word |
| Scope statement | 4 | Word |
| WBS | 4 | Word |
| WBS dictionary entry | 4 | Word |
| Activity list and attributes | 5 | Word |
| Milestone list | 5 | Word |
| Activity resource requirements | 5 | Word |
| Project schedule | 5 | Project |
| Cost estimate | 5 | Excel |
| Cost baseline | 5 | Excel |
| Quality management plan | 6 | Word |
| Quality metrics | 6 | Word |
| Quality checklist | 6 | Word |
| Project organizational chart | 6 | PowerPoint |
| RACI chart | 6 | Excel |
| Resource histogram | 6 | Excel |
| Human resource plan | 6 | Word |
| Communications management plan | 6 | Word |
| Project Web site | 6 | FrontPage |
| Risk management plan | 6 | Word |
| Probability/impact matrix | 6 | PowerPoint |
| Risk register | 6 | Excel |
| Make-or-buy analysis | 6 | Word |
| Procurement management plan | 6 | Word |
| Request for proposal | 6 | Word |
| Contract statement of work | 6 | Word |
| Supplier evaluation matrix | 6 | Excel |
| Milestone report | 7 | Word |
| Change request | 7 | Word |
| Cause-and-effect diagram | 7 and 8 | PowerPoint |
| Team roster | 7 | Word |
| Team performance assessment | 7 | Word |
| Issue log | 7 | Excel |
| Qualified sellers list | 7 | Word |
| Contract | 7 | Word |
| Earned value chart | 8 | Excel |
| Deliverable acceptance form | 8 | Word |
| Run chart | 8 | Excel |
| Scatter diagram | 8 | Excel |
| Histogram | 8 | Excel |
| Pareto chart | 8 | Excel |
| Flow chart | 8 | PowerPoint |
| Performance report | 8 | Word |
| Customer acceptance-project completion form | 9 | Word |
| Final project report table of contents | 9 | Word |
| Transition plan | 9 | Word |
| Lessons-learned report | 9 | Word |
| Contract closure notice | 9 | Word |
| Potential project | App B | Word |
| Draft schedule | App B | Excel |

Figure B-1. Templates available for download on the companion Web site

The last two templates can be used for proposing real projects and preparing a draft project schedule in Excel, software most students are familiar with, before creating one in another tool, such as Project 2013. Figures B-2 and B-3 show screen shots of these two templates.

Potential Project Proposal

Student Name:	Date:					Date:

Potential Project Name:

Project Sponsor’s Name, Organization, and Contact Information:

Justification or Reason for the Project:

Main Project Deliverables:

Required Team Skills:

Main Team Tasks/Roles:

My Desired Role and Why:

Project Sales Pitch:

(You must convince at two and up to four of your classmates to work on this project with you. Write a short sales pitch to read in class.)

Figure B-2. Potential Project Proposal

Figure B-3. Draft schedule template

# Case Studies

Each chapter of this text includes Exercises and Team Projects, but some instructors like to assign more detailed case studies. This section provides three running case studies: Real Project, New Business Venture, and RMR Team Co-location. You can also find further suggestions for using real projects or other case studies, such as those provided by the Harvard Business Review, on the companion Web site for instructors under “Teaching Ideas.” There are also links to samples of completed student projects on https://sites.google.com/site/profschwalbe/ along with instructions for creating a Google site.

The first running case provides two individual homework assignments to solicit real project ideas from each student and to assess the team project. It then provides detailed instructions on what is required for the real projects. The other running cases include five parts—initiating, planning, executing, monitoring and controlling, and closing—with scenario-based information and several tasks to complete under each part. Students can refer to the sample documents found in the text to help them complete the tasks. Several of the tasks involve using templates provided on the companion Web site. Anyone can use these cases as long as they mention the source. Feel free to modify them to meet your class needs.

## Case Study 1: Real Projects

Note: My personal preference (Kathy Schwalbe) is to use real projects as part of a project management class. It helps students gain real-world experience and practice working with a “real” sponsor and other stakeholders. Projects often produce very useful results for the college, non-profit organizations, businesses, or the students themselves. The information below is based on my personal experience and syllabi instructions for having students work on real projects in a team setting. I give students the option of doing another case study, but the vast majority of students choose to work on a real project.

An important part of coming up with good project ideas is the following required homework assignment, due very early in the course. Each student must do the homework, so as long as you get about one good idea out of every four, you should have enough real projects to work on. I often propose additional project ideas, mostly from suggestions from colleagues or former students.

### Individual Homework: Project Proposal (100 points)

Here’s your chance to get some useful work done! Each student will propose a project to be done as part of this class, and hopefully we will do several of them.  Even if you want to do a case study instead of a real project, you must still propose a real project. Projects must have a sponsor (can be a student, friend, relative, boss, community leader, etc.), provide a needed service or product, and be a good fit for this class. Each student normally spends between 20-40 hours on the class project. Look at some of the past student projects and the information in the syllabus about the projects.  Then write a proposal for a potential project, using the potential project template. Talk to the sponsor before writing the proposal, and try to come up with a good proposal! Think about projects at work, for community groups, etc. that you could do. If you do not do a real project, you will work on a case study. You still need to propose a real project, though, to get experience doing that!

It is also important to explain how grades will be determined for these team projects. Below is another individual homework assignment that allows each student to provide inputs on his/her own team project grade and the grade of each team member. They do this assignment for both the real projects and case studies, and it is due the last day of class.

### Individual Homework: Self Assessment (100 points)

Write a 1-2-page self-assessment based on the team project, answering the following questions:

- If you had to give your team a grade for the project, what would it be?  Why?

- What were your roles and responsibilities on the group project?  How well do you think you performed on this project?

- Briefly assess each team member’s performance.  If you had to give each person, including yourself, a grade, what would it be and why?  To compare individual contributions, if you had 100 points to allocate to your team, how would you allocate them?  If you’re an Apprentice fan, what would be the order you would use to fire people from your team?

### Syllabus Description of Team Projects

The purpose of the team project is to use a structured approach to project management in a team setting (3-5 students/team). I normally let teams self select and assign people to teams as needed. One person could take the lead on each task, but other team members should provide inputs and edit the work so it is consistent and of high quality and reflects a team effort. Each team member should plan to spend 20-40 hours total on the team project, including some time in class. If the project is done for someone outside of Augsburg, students can earn the Augsburg Experience credit. You must have the sponsor call or email me to approve the project after you propose it if you really want to work on it. The sponsor must also provide feedback to me before the second progress report and final presentation. If you do not choose to work on a real project, teams will work on one of the other case studies. You can substitute a different business idea for the new business venture case study, if you like, with my approval.

Examples of “real” class projects: As you can imagine, there can be a wide variety of real projects. I starting requiring team project Google sites starting in 2011 and postted just a few. Some examples of recent class projects include the following:

- Doing a project for an employer, such as implementing a marketing plan for a new business, analyzing a business process and recommending improvements, etc.

- Organizing and running a fundraising event, like the Hockey Team Fights Cancer project (raised over $5,000 one fall), a campus yard sale/fundraiser, a benefit for someone with a disease, a 5K race for the Make a Wish foundation, or making baby blankets for hurricane victims

- Creating/updating a Web site or smart phone/table app for a small business or non-profit organization

- Helping your college perform a project, like a project to change food service suppliers, a special job fair, a major event, etc.

Team Progress Reports:

If you are working on a case study, I’ll provide instructions on which tasks you should have completed by the progress report dates and which ones to present. Below are instructions for what is needed for progress reports for the “real” projects. I will review some of this information before you present as part of an online assignment. I also want to communicate directly with your project sponsor and have comment access to your team’s Google site at least a week before your first progress report.

Progress Report 1: Assume you, the project manager, are giving a formal progress report to senior managers. You will present and review highlights of the following information:

- a brief introduction of your project and your team, emphasizing why you are doing the project, what your main deliverables will be, and how you will measure success

- a one-page progress report (using the template called performance report)

- a project charter (using template), signed by all stakeholders, including your sponsor (an email confirmation is okay in place of a signature for now)

- a summary of communications so far with your project sponsor and instructor (emails or documented meeting minutes)

- a preliminary scope statement (using template. Note: Desribe each product-oriented deliverable using at least two complete sentences)

- a team contract, emphasizing the communications section (using template)

- a draft schedule (using the template). Focus on what you have under Executing and your total estimated hours by person. This is a rough estimate, but do the best you can for now. Your team can update actual hours using Google docs or other means.

- a brief summary of your team’s MBTI types and how it might affect your team dynamics (Note: You should include an assignment for each student to take the MBTI).

Be sure all of your documents and your presentation are on your team’s Google site under a section called Progress Report 1. Put key information from each document in a presentation and make sure it is easy to read. For example, you can paste the information from all of these documents into PowerPoint slides. You can also pull up some of the documents and zoom in so they are easier to read, like the draft schedule. Make sure you have consistent information in each document. For example, if you say in your project charter under the approach that you will prepare a flyer for your project, describe that flyer in more detail as a deliverable in the scope statement and include it in the executing section of the draft schedule. It would probably fall under a summary category called marketing. I will provide written and verbal feedback during the presentation, just as a program manager would, and also add comments on your Google site.

Progress Report 2: Assume you, a team member, are giving a formal progress report to senior managers. Be sure all of your documents and your presentation are on your team’s Google site under a section called Progress Report 2. You will present and review highlights of the following information:

- a one-page progress report (using the template called performance report. Be sure to focus on work completed since the first progress report)

- an updated scope statement, including more detailed descriptions of key deliverables

- a Gantt chart created in Microsoft Project, based on the draft schedule you created. Be sure to include your detailed WBS under executing, and list at least 4 milestones under executing. Note: You can create the Gantt chart in MindView, if you prefer.

- a probability/impact matrix, including at least 10 potential risks for your project. For at least three of them (most important ones), describe your strategy for managing them in writing

- a summary/sample of completed deliverables under executing

- a comparison and explanation of estimated versus actual hours to date (show your updated draft schedule)

- feedback from your sponsor since the last progress report

Final Project Presentations and Notebooks

By the last day of class, each team will present a final project presentation and hand in a project notebook (stapled pages or soft cover - no spiral notebooks, please). Assume you are giving a presenation to senior managers and potential employers. If you do a case study, put all of that information together in a notebook. If you do a real project, include the following information. All documentation should also be available on the team’s Google site under a heading called Final Presentation. Note: Each team member must give part of the 20-30 minute final presentation.

- Cover page and detailed table of contents.  List the project name, team members, and date on the cover page of the notebook.  Be sure to number all pages (by hand is fine), which should match the table of contents.  You may include tabs or dividers between major sections of the notebook, too.

- A double-spaced 3-4-page project report.  Address the following questions in your report, which should be in the front of your notebook after the table of contents:  What did your team produce?  Was the project a success or not, and what was your criteria for determining success?  (Remember that should be defined in your scope statement early in the project). What project management tools/documents did you use, and did they help? How close was your draft schedule and estimate of hours to the actual schedule and actual hours worked on the project?  What went right on the project?  What went wrong?  What did your team learn by working on this project?  How did you select the project manager? Did he/she do a good job at leading your team?  Did you work well as a team? What was your project sponsor’s final assessment of the project? Include some written feedback from the sponsor in your final report and presentation. See the sample customer acceptance form in your text for an example. Discuss this information in your final project presentation and show/summarize the main products produced. If your project involves some type of event, be sure to show pictures of the event.

- Hard copies of all of the products your team produced. Include the project management documents you created (charter, Gantt chart, etc.), communications with your sponsor, and all product-related items.

Note:  Part of the grade for the team project will be based on the team’s final presentation and progress reports, and part of grade will be based on the quality of the project and its notebook (one notebook per team, due the last day of class).  You should also include a project completion form or some method of evaluation for real projects. I will look at the final homework where everyone suggests grades as well. Team project managers will earn a small amount of extra credit for successfully leading their project teams.

## Case Study 2: New Business Venture

This case should be interesting to anyone interested in starting a new business. It involves research, marketing, finance, technology, and personal ethics. Feel free to change the type of business, if desired. The main purpose of this and other cases, however, is to help you practice some of the project management skills you are developing as part of your course. Note: If students want to propose a different business idea, let them! You can still use many of the tasks listed below, but modified as needed.

### Part 1: Initiating

Background Scenario:

You and some of your friends/colleagues have been working for large organizations for many years, but several of you have a desire to start your own business. You have decided that you are ready to pursue your idea of starting a healthy kids club focusing on helping children age 8-18 to develop healthy eating and exercise habits. You are thinking about opening one physical center and developing a Web site for the business in less than a year. You would focus on your local area first, emphasizing healthy weight loss, and then expand to other parts of the city, the state, and beyond if things go well.

This New Business Venture Project would primarily involve you and four of your friends/colleagues:

1.	You have a medical background as a nurse. You love patient care, and you are disheartened at the number of people you see with problems that could have been avoided. You have struggled with weight issues all of your life, but you work hard to maintain a healthy weight and exercise regularly. You know of many programs geared towards adults, and you successfully lost 30 pounds a few years ago through one and kept it off. But there are very few programs for children, especially as they go through puberty, which is a crucial time for developing good habits.  You cut back your hours to half-time five years ago, working mostly on weekends. Your children are now 16 and 18, so you have more free time and have always wanted to start a business. You also love to write and blog about living a healthy lifestyle. Your sister, Tina, loves the idea and said her daughter would be one of your first customers.

2-3. Tom, an accountant, is one of your neighbors. His wife, Emma, works part-time as a nutritionist for a popular weight-loss company (the same one that helped you lose weight). Tom and Emma love the idea of opening a business targeting children, as they have two young children of their own. They could both provide advice, but they would want some ownership in the business.

4.	Olivia, one of your best friends since sixth grade, is currently working as a part-time marketing consultant/web designer. She is very tech-savvy and willing to work part-time on this new business venture, for a fee. She said she’s offer a lower rate at $40/hour.

5.	Calvin currently works as a physical education and health teacher at your local middle school. He has a lot of contacts with local parents and teachers and can talk to anyone about very personal issues. He is single and would want to keep his current job, but he could devote a fair amount of time to the business in the evenings, on weekends, and in the summer. He is not sure how he’d want to be paid yet, but is leaning toward some type of hourly pay.

The main objectives of the New Business Venture Project are to prepare a business plan, develop marketing materials (including an initial Web site and brochure), and find a few good locations for the initial site. Your goal would be to determine if this would be a good business opportunity.

Work with your teammates and instructor to perform all or just some of the following initiating tasks for this project.

Tasks

- To become more familiar with the children’s weight loss/health market, do some preliminary research to find out how big this market is, who the main companies are in the market, what the best-selling products and services are (i.e. food products, counseling, exercise classes, camps, etc.), pricing and marketing strategies, etc. If you do not want to focus on your own geographic area, pick one to focus on for this and future tasks. Write a 500-800 word paper with your findings, citing at least three references.

- Research how to write a good business plan. Write a 500-800 word paper with your findings, citing at least three references. Also document any questions or concerns you have about writing one for this business. You will need to be creative and make several assumptions, especially in the financial section.  You should provide a spreadsheet with a start-up cost estimate and 3-year financial projections where inputs can easily be changed (i.e. number of customers, average revenues/customer/week, etc.).

- Prepare a stakeholder register and power/interest grid for the project. Include all project team members and make up names and information for at least one other spouse, one potential financial backer, and one local competitor. Assume that you and your four friends/colleagues are all team members. You are willing to invest $20,000 yourself, and Tom said he might do the same if the numbers look good and he and his wife would get a large equity stake in the company.  You are not sure how much start-up funds you would need yet.

- Prepare a team contract for this project, emphasizing the communications section.

- Prepare a project charter for the project. Assume the project will take six months to complete. Recall that the main project objectives are to prepare a business plan, develop marketing materials, and find a few good locations for the business.  Be sure to decide on a good name for the business.

Progress Report 1: Assume you, the project manager, are giving a formal progress report to senior managers. You will present and review highlights of the following information:

- a brief introduction of your project and your team, emphasizing why you are doing the project, what your main deliverables will be, and how you will measure success

- a one-page progress report (using the template called performance report)

- all of the initiating tasks above a summary of communications so far with your instructor (emails or documented meeting minutes)

- the first four planning tasks listed in the next section

### Part 2: Planning

Work with your teammates and instructor to perform all or just some of the following planning tasks for this project.

Tasks

- a preliminary scope statement (Note: Desribe each product-oriented deliverable using at least two complete sentences)

- a team contract, emphasizing the communications section (using template)

- a draft schedule (using the template). Focus on what you have under Executing and your total estimated hours by person. This is a rough estimate, but do the best you can for now. Your team can update actual hours using Google docs or other means.

- a brief summary of your team’s MBTI types and how it might affect your team dynamics (Note: You should include an assignment for each student to take the MBTI).

- Create a milestone list for this project, and include at least 10 milestones and estimated completion dates for them. Be sure to provide good drafts of key deliverables that your instructor can review.

- Use draft schedule and milestone list you developed in numbers 3 and 4 above to create a Gantt chart in Project 2013, MindView Business, or other software. Estimate task durations and enter dependencies, as appropriate. Remember that your scheduled goal for the project is six months.

- Develop a cost estimate for leasing the space with furniture, buying one computer  with software for logging customer information and processing payments, and 2 scales that measure body fat very precisely.  Assume you need at least a seating/reception area, one large room that can hold 20 people, at least 3 smaller rooms for offices/consultations, and a storage area. You would consider using part of a school, church, or community center to lower costs. These costs will be a major part of your start-up costs.

- Create a quality checklist for the initial Web site you will develop.

- Create a probability/impact matrix and list of prioritized risks for the project. Include at least 10 risks, and summarize your strategy for two important ones.

Progress Report 2: Assume you, a team member, are giving a formal progress report to senior managers. Be sure all of your documents and your presentation are on your team’s Google site under a section called Progress Report 2. You will present and review highlights of the following information:

- a one-page progress report (using the template called performance report. Be sure to focus on work completed since the first progress report)

- an updated scope statement, including more detailed descriptions of key deliverables

- planning tasks 5-9

- a summary/sample of completed deliverables under executing (be sure to have a good start on each deliverable)

- a comparison and explanation of estimated versus actual hours to date (show your updated draft schedule)

- feedback from your instructor since the last progress report

### Part 3: Executing

Remember that the main objectives of the New Business Venture Project are to prepare a business plan, develop marketing materials (including an initial Web site and brochure), and find a few good locations for the initial site. Your goal would be to determine if this would be a good business opportunity.  Work with your teammates and instructor to perform all or just some of the following executing tasks for this project.

Tasks

1.	Write a business plan for this project. Be sure to use the information you found under the initiating task and review sample business plans. Decide on a name for this business, as well. Include, at a minimum, the following sections in a five- to eight-page paper:

- Executive Summary

- Company Description

- Products and Services

- Marketing Plan

- Operational Plan

- Management Summary

- Financial Plan (including an estimate of all start-up costs and 3-year financial projections)

2.	Create a brochure for your new business and an initial Web site. The Web site should include, at a minimum, a home page, an about us page, and a description of products and services.

3.	Research options for a rental space for the business. Develop at least five alternative sites. Include a picture of the site, if available, square footage, cost, pros and cons, etc. Document the results and make a recommendation for which site to select in a three- to four-page paper. You need to decide on the site to do your cost estimate and financial projections. You also need a better idea of products and services to decide how large a space you need. Assume you need at least a seating/reception area, one large room that can hold 20 people, at least 3 smaller rooms for offices/consultations, and a storage area.

### Part 4: Monitoring and Controlling

Background Scenario:

Assume that the following has occurred since the project started: As planned, you took the lead of the project, but you’re starting to get burned out. You are three months into the project. You are still working your half-time job, and your spouse has been complaining that you work too much and aren’t delegating enough. Olivia was supposed to have a draft of the brochure and Web site ready, but no one can agree on the main products and services you’ll provide, so you only have a few templates so far. Olivia has already billed you for 30 hours of work, mostly from attending your team meetings, which are not always productive. Calvin promised to get a big list of potential students and parents to you for the past two months and research competitors, but he still hasn’t provided anything in writing yet. He has also missed about half of your meetings (you try to meet every other week for 2-3 hours). Lyn seems to want to go in a different direction than you by developing a brand new food line. Tom has not been much help and wants a 50% partnership agreement before he’ll do much work, and you were counting on him to do the cost estimates and financials. Tom and Calvin seem to disagree on a lot of key decisions, especially the best location and pricing issues.

Work with your teammates and instructor to perform all or just some of the following monitoring and controlling tasks for this project.

Tasks

- Write a two- to three-page paper describing how you would handle the challenges listed in the background scenario.

- Create a new Gantt chart based on the revised information above, if needed. Briefly describe other plans you have created so far that you think you should update in a one- to two-page paper.

- Prepare an agenda for a team meeting to discuss several of the issues you are facing. You definitely want to decide on the location at this meeting, since it is down to two and you have to decide soon. Also write a one- to two-page paper summarizing how you will approach particular people during the meeting.

- Review the Seven Basic Tools of Quality. Based on the current project scenario, pick one of these tools and create a chart/diagram to help you solve problems you are facing. Use the templates and samples provided.

- Update your list of prioritized risks. Create a risk register entry for two of them.

### Part 5: Closing

Background Scenario:

You did get everyone to work together to complete all of the work, but your estimated start-up costs are much more than the $40,000 you and Tom are willing to invest. The financial projections are much better than you thought, though, so you are trying to decide what to do next. Tom suggested that you present your business ideas to a small group of people you think might invest in it.

Work with your teammates and instructor to perform all or just some of the following closing tasks for this project.

Tasks

1.	You have scheduled a presentation for potential investors. Prepare a 2-5-minute sales pitch, similar to what you might see on the television show “Shark Tank.”

2.	Prepare a 20-minute slide presentation to summarize the results of the project. Show all of the work not presented in earlier progress reports. Include a list of lessons learned for the entire project and summarize the estimated versus actual hours.

3.	Prepare a final project notebook documenting all of the work you did. Include a cover page and table of contents.

# Case 3: EMR Team Co-location

This case should be interesting to anyone who oversees facilities at a healthcare provider, or, to any project or program manager who may be looking to co-locate a project team into a common area. This case involves research, procurement, finance, construction, and technology.

The main purpose of this and other cases, however, is to help you practice some of the project management skills you are developing as part of your course. (Note: Instructors should feel free to modify background information or tasks. You can have two progress reports like the above two cases, for example. This case is based on a true story provided by Dan Furlong.)

### Part 1: Initiating

Background Scenario:

Gartner, the large technology research organization, has suggested that project teams that are co-located have a 400% higher chance for success than a team that is forced to work virtually (team members spread across several buildings, cities, or countries). You may remember that co-location is defined as project team members sharing a common space, whereby virtual teams are defined as teams spread across several buildings, cities, states, or countries.

You have just been named the program manager for an EMR implementation project for an academic medical center. This project is expected to be the largest non-construction project in the organization’s history. Largest in cost, largest in the number of staff members engaged, and the largest in the impact to the organization. This project is considered a central component of the organization’s strategic plan, and critical to the organization meeting Stage 2 meaningful use requirements.

As you work with the EMR vendor to identify required resources, you and your PMO calculate that the team will consist of 97 to 100 full time team members – a large team by your organization’s standards, and probably by any healthcare organization’s standards. The staff will be grouped by major healthcare function– revenue cycle, inpatient clinicals, and outpatient clinicals – with each of those areas being further subdivided into smaller projects.

In total there will be fourteen separate projects, with fourteen separate project managers, with an additional six managers overseeing the project managers, and four directors overseeing the managers. The program team will also include you, the program manager, the PMO and his staff, and a communications manager. These last two positions will report directly to you, while the remaining managers and project managers will report to you for the project, which they will be committed to for the next several years, but to the directors for their administrative non-project needs (performance reviews, time off, pay raises, etc.).

Since communication comprises 50 to 80% of the project manager’s job, and lack of effective communication is one of the primary causes for project failure, this program’s success will be put into jeopardy due to the great number of resources involved – communications will be complex.

You and the PMO decide that this program will not succeed without the team being co-located. There are simply too many areas where the fourteen different projects cross over for them to be spread out across the organization’s many buildings across the city. Together you make this recommendation to hospital leadership, and they agree to look for space for the team. No guarantees, but they agree that co-location would be best. They also agree that if they can’t find space that they own, that they would consider leasing space for the team, as close as possible to the main campus.

Work with your teammates and instructor to perform all or just some of the following initiating tasks for this project.

Tasks

- Research the office space market in your area for space large enough to house the team of 99 team members in a cubicle environment. This space should also include approximately twenty offices for the managers, directors, and program leadership along with a break area, a copier room, storage space, and four conference rooms large enough to hold twelve people each. The space must be ready for occupancy within six months and allow a lease of three years. Prepare a short paper and/or presentation on the market, the expected leasing costs over three years, and include any expected renovation costs.

- Find at least three references about the drawbacks of short term leases (less than five years), and three more about team co-location benefits. Uses these references, the synthesis of information found in them, combined your own opinions, prepare a short paper and/or presentation about the pros and cons of co-location of teams on-site versus off-site for large projects. Be sure to identify when you are drawing your own conclusions based on the evidence and when you are citing references.

- Talk to a local office supply company about the costs to provide furniture for the project team. The furniture should include everything needed for 99 cubicles, twenty offices, and the four conference rooms. Consider different options for the furniture (different quality levels, perhaps). Prepare a short paper and/or presentation about the expected costs, including any cost variables, required to supply the furniture for the team.

- Prepare a stakeholder register and power/interest grid for the project. Include all project team members and make up names and information for the following: you, the PMO, the four directors (they may be grouped into one), the team members (they may also be grouped), and hospital leadership (also grouped).

- Prepare a project charter for the EMR Team Co-Location project. Assume the project will take nine months to complete, but use your cost estimates for the furniture and leasing for your cost figures. For technology, budget $4000 per person initially to cover PCs, telephones, networking, and conference room audio-visual equipment. The first month of the project will involve finding the property; the second month will involve the leasing paperwork; the third month the office design work; and the remaining six months will involve renovations and furniture installation. Assume the project will start on January 1st and ends on September 30th, so that the project team can move in on October 1st.

- Prepare an initial scope statement for the project. Assume that all work on the facility will be managed by the owner of the facility, but that your PMO will oversee the work itself. The PMO will attend weekly construction update meetings, work with the designer to pick the furniture, and coordinate any technology needs through your own IT department. Technology needs include desktop PCs and phones for each person, a copier for the copy room, one color laser printer for every 20 people, and audio-visio equipment for the four conference rooms. The kitchen equipment will be provided by the property owner as part of the renovation.

- Complete a draft schedule in Excel for your class team to work on this case study.  Include all of the activities in this case study using the main categories of initiating, planning, executing, monitoring and controlling, and closing. Break down the executing work to what you think is an appropriate level. The main executing deliverables should be a renovation cost estimate, renovation schedule, rental strategy, and financial spreadsheet. Be sure the WBS is based on the project charter, scope statement, and other relevant information. Estimate how many hours each of your team members will spend on each task in the Excel file.

- Pulling together the above presentations that you created, prepare a ten-minute presentation to summarize results from the initiating phase of the project. Assume the presentation is for a management review to decide if the project should move on to the next phase. Be sure that all of your project documents are on a Google site that you share with your instructor for viewing and commenting only.

### Part 2: Planning

Background Scenario: Your PMO worked with your organization’s leasing office to find an acceptable location just two miles from your main hospital. The space has enough room for 107 cubicles and 22 offices, which allows for a bit of unplanned growth if needed. It also already had eight offices, a kitchen, a copy room, and six conference rooms in place from the previous tenant. However, the kitchen was too small and two of the conference rooms were very small, holding only four people at a table.

The property owner suggested that one of the two small conference rooms be used for storage, which you agreed to since it was near the copy room. They also suggested that the second small conference room, which is adjacent to the kitchen, be combined with the existing kitchen to make one larger kitchen and break room area. The property owner then suggested that he build twenty-two offices, instead of twenty, to allow for some growth. Last of all, he suggested that we only install 100 cubicles, but that we design the space for 107 so that we can add more later if needed, without having to move existing furniture later.

The property owner estimates that the renovation costs will be $448,000, but he asked for a 10% contingency to allow for unknowns. After having your own leasing office and facilities team review his estimate, everyone agreed it was accurate given what we know today. Both the property owner and your PMO agreed that any changes to the contract should require a written change order, signed by the property owner, your hospital’s PMO, and your hospital’s legal office. There would be no leasing costs during the renovations – the monthly leasing does not start until thirty days after renovations are completed, or when the team moves in – whichever comes first.

For the furniture, your PMO contacts a local design company that your organization has used multiple times. The design company charged $5,000 for their services, but they guaranteed that they will save at least this much by an efficient use of cubicle panels and other components. They quoted the furniture at $328,000, including installation, and noted that it will take six weeks for the furniture to arrive and two weeks to install it. They asked that we not order the furniture until the renovations are eight weeks away from completion, as they do not have the space to store the furniture for more than a couple of weeks prior to installation.

Work with your teammates and instructor to perform all or just some of the following planning tasks for this project.

Tasks

- Develop a requirements traceability matrix and a more detailed scope statement for the project.

- Create a milestone list for the executing part of the co-location part of this project, and include at least 10 milestones and estimated completion dates for them. Assume that you start looking for space on January 1st, sign the lease by February 28th, start the design work March 1st, and start renovations April 1st for an October 1st move in date by the team. You should include the team moving into the space as part of this project, and allow them two weeks to complete the move in.

- Use the WBS you created earlier, the milestone list you developed in task #2 above, and any other information provided to create an initial Gantt chart and network diagram in Project 2013, MindView Business, or other software. Create one Gantt chart for the actual co-location renovation project described in this case, assuming a start date of January 1 and end date of September 30 for the renovations, and another two weeks for moving in the team. Create a second Gantt chart for your team to do this case study, including all the project management tasks and the dates of your class for them. Remember to include dependencies between activities. Estimate activity durations and enter dependencies, as appropriate. Print the Gantt chart and network diagram.

- Create a quality checklist for ensuring that the co-location renovations go well. Also define at least two quality metrics for the project.

- Create a RACI chart for the main tasks and deliverables for the project, focusing on what you and your class mates need to do.

- Create a probability/impact matrix and list of prioritized risks for the renovation part of the project. Include at least 10 risks.

- Develop a cost estimate for all renovations, using the numbers below. Include all costs, including internal costs, in your estimate:

| Description | Cost per Unit | Number of Units Required | Source |
| --- | --- | --- | --- |
| Renovations | $448,000 | Fixed Price with 10% contingency | Property Owner |
| Designer Services | $50/hour | 100 hours | Office by Design Services, LLC |
| Furniture | $328,000 | Fixed Price | Smith Office Furniture |
| PCs | $1200 | 131 | Internal cost |
| Phones | $300 | 131 | Internal cost |
| Copier | $23,000 | 1 | Eastern Office Supplies |
| Audio-Visual | $23,820 | 4 | CityCom AV |
| Network Lines | $192 | 260 | Internal Cost |

- Prepare a ten-minute presentation that you would give to summarize results from the planning phase of the project. Assume the presentation is for senior hospital management, who must decide if they want to lease this space in order to allow the team to co-locate or to just let the team be squeezed in wherever it can in their existing facilities, basically creating a virtual team for the EMR project that will begin in October.

### Part 3: Executing

The project to lease the off-site space was approved by leadership, and you have been given the go-ahead to start. The hospital’s CEO directed your sponsor, “Do what needs to be done to ensure that we can start the EMR project on October 1st. We must start the EMR project on time!”

Your project team consists of three staff from your facilities and engineering department, two intern volunteers from the PMO, three staff from the networking team, and four staff from the PC installation and support team. In addition, the PMO will manage the team, and although not overseeing the construction crew themselves, the PMO will have to coordinate the construction work with the work that the internal teams will be performing (network lines and equipment, pc installation and setup, office supply ordering and distribution to cubicles and offices, and then moving in the EMR team).

- During executing you are doing the work that you planned. In a one-page paper, describe the activities that you would be doing as you execute the work required for the EMR Co-Location project. From your paper create a one- or two-slide presentation that highlights the work being completed during this part of the project.

- In a short paper, describe what team building methods you would use to bring together this diverse group of team members so that they all understand their importance to the project, and, so that they all better know one another – in other words, how would you bond this team together – and why? Add one to three slides to your previous presentation to describe the steps you will take and the reason why you feel it is important to take these steps.

- This project includes all work around the renovations, from choosing a location to designing the space to renovating the space to installing furniture to installing required technology. The project sponsor also wanted this project to include the moving of the EMR project staff to this newly renovated space. In a one-page paper, briefly describe why (/why not) it was reasonable to include the staff moving as part of the renovation project. Include references, if possible, and add important points to your presentation.

### Part 4: Monitoring and Controlling

Background Scenario:

When the landlord is done with renovating the work spaces your PMO realizes that only one conduit was run to each island of cubicles. The missing conduit was to be used to run the low voltage networking cables to the cubicles, as low voltage wires may not be run alongside the high voltage power lines, which have already been pulled through the single conduit already in place.

One of the interns, who is overseeing the PC orders, informs the PMO that the PCs will not arrive until September 28th, three weeks late and just three days prior to the move in date of October 1st. The delay is due to a fire in a processor chip plant in Singapore, and although a different brand of PCs could be ordered, the organization only uses this brand in order to minimize maintenance issues long term. The PMO had originally planned to use all four people on the PC team for ten days to install the desktop computers, and now they will only have three days (assuming the PCs are not further delayed).

Work with your teammates and instructor to perform all or just some of the following monitoring and controlling tasks for this project.

Tasks

1.	Discuss with your team members how you can get the required network access to the cubicles. Research different methods available for providing network access to desktop computers, and identify at least three options for providing the required access. Prepare a one- to two- page paper summarizing the information and add the salient points to your presentation.

2.	The PCs arriving three weeks late are of great concern and can cause the EMR Co-Location project to be late, as well as delaying the upcoming EMR project kickoff in September. Brainstorm with your team to identify at least three options for ensuring that the project will not be late.

3.	Review the Seven Basic Tools of Quality. Based on the current project scenario, pick one of these tools and create a chart/diagram to help you solve problems you are facing.

4.	Update your list of prioritized risks. Create a risk register entry for two of them.

### Part 5: Closing

Background Scenario:

It is September 30th and the PMO just informed you that the new space is ready for move in by the EMR team. The PMO notes that the move will begin on September 1st and end on September 5th, as originally planned. There are a few loose ends, however, that will have to be completed after the move in is completed. For example, four of the cubicles are missing their hutches, one of the two refrigerators was damaged and so only one is installed, and the water chiller for the water fountain did not work when installed.

The hutches will not arrive for four weeks but the hospital will use stock ordered for another area for this project, and then backfill their stock with our hutches when they do arrive. However, they want to wait until the team is moved in so they will install the hutches on September 6th, a Saturday. The water chiller has had a warranty request submitted and the plumber will replace it by September 10th, and the second refrigerator will be installed by September 14th.

Work with your teammates and instructor to perform all or just some of the following closing tasks for this project.

Tasks

1.	The project sponsor is excited about how well this project went. Despite a few hiccups, the EMR team will move in on time and that means that the EMR project will kick off on time (or, at least it won’t be our fault!). She has asked that you prepare a two page executive summary that describes the initial project goals, planned versus actual scope, time, and cost information, and an overview of challenges faced. She also wants a ten- minute presentation that covers the same points and in the presentation she wants to see before and after pictures (be creative in finding pictures) of the space.

2.	Prepare a lessons-learned report for the entire project, focusing on what you and your class mates learned about project management. Include input from all stakeholders in summarizing the lessons learned.

3.	Prepare a final project report, using information from progress reports and your final project presentation and the template provided. Be sure to include who and how the last few loose ends will be monitored for completion and how the project team members were released back to their respective teams. Be sure to include all of the documents you have prepared as appendices.

# Simulation Software

Another way to practice your project management skills is by using simulation software. There are several tools available, including three listed below. Note that all are separate purchases.  These tools are all Web-based and cost $20- $40 per student with discounts for mentioning this book. Consult the suppliers for more details. If you find better ones or have suggestions on using these tools, please let me know at schwalbe@augsburg.edu.

1. Harvard Project Management Simulation: Scope, Resources, Schedule (http://hbsp.harvard.edu) now provides a web-based tool to help students apply their project management skills in a simulated environment.  The price listed in 2013 was $37.50. Most students can run the simulation once within 90 minutes and benefit from running it again. The following information was taken from their Web site in June, 2013.

The second release of this simulation adds a new scenario with multiple unanticipated events and the ability to add prototypes to the project plan. In this single-player simulation, students take on the role of a senior project manager and manage a team tasked with developing a new product for an electronics manufacturing company. The primary objective is to execute a project plan successfully and deliver a competitive product on time and on budget. Instructors can assign up to 6 scenarios that expose students to realistic challenges that project managers often face, especially when working in a highly competitive industry. Some challenges require students to react to unanticipated outside events, such as a staffing crisis, while others require students to respond to strategic changes mandated by upper management. A new project lever for specifying prototypes allows students to explore the benefits of this essential component of agile project management.

2. Fissure (www.fissure.com) now provides a web-based tool to help students apply their project management skills in a simulated environment.  The price listed in 2013 was $44.99, and you should be able to get a discount for mentioning this book. Most students can run the simulation once within 2-3 hours and benefit from running it again, taking another 1-2 hours. The following information was taken from their Web site in June, 2013.

SimProject®, is an online project simulation (both the technical and human aspects) from Fissure Corporation used by many academic institutions around the world as part of their project management curriculum. SimProject, the Alliance Prototype project has 7 tasks and 10 potential team members. SimProject can be given as standalone home work for students (individual or teams), or utilized as a classroom activity with teams of three or four students sharing the role of project manager. Purchase includes three runs or complete executions of the simulated project. SimProject will expire after the third run or after 120 days (even if all runs are not completed).

3. Double Masters (www.doublemasters.com) provides a project management simulation for academia.  Instructors should contact info@doublemasters@com and mention this book to receive a discount on the academic version.  The price in June 2013 was $29.95 per student (without the discount). Most students take about 7 hours to run the entire simulation. The following information was taken from their Web site in June, 2013:

Double Masters simulations are offered via the web on demand and can be run whenever convenient for the student or instructor. This means there is no software to download or manage and the simulation can be accessed from any computer in the world, as long as there is Internet connectivity.

The process is simple and straightforward:

- An instructor will sponsor a session: a session ID and access code are generated in order to group students into a single online course

- The instructor defines the session duration: start and end date for student accessibility

- The students create a user account and register for the session identified by their instructor

- The students can only run the simulation during the established time constraints of the simulation

The simulation provides each student with detailed feedback, using various metrics to gauge the effectiveness of his or her decisions. A Scorecard is available to both the student and instructor with a final score out of 100.

4. Sandbox Model (www.sandboxmodel.com) also provides a simulation tool. The price in June 2013 was $50 per student, and you should be able to get a discount for mentioning this book. Most students can run the web-based simulation once within 30 minutes. The following information was provided in June, 2013.

- The simulation engine has scientific foundations that are based on reality.

- Variability – choose between different modes of execution for the project.

- Real world case studies are built into the PTB™ database.

- Simulation makes project management training efficient, enjoyable and saves money.

- Using the PTB™ improves project results and increases your organization’s profit.

- Advance simulation time to receive immediate feedback and see the impact of your decisions.

- The History mechanism allows you to learn from past mistakes and to duplicate successful solutions.

- The "learn by doing" approach allows you to acquire knowledge that is not easily forgotten.

- The PTB™ integrates different topics of project management into one complete tool. You get a chance to see how everything connects through active hands-on training, rather than by listening to lectures.

- The PTB™ provides a simple yet effective interface with other project management software. Import projects from other software and run a simulation to test them.

- The simulation is controlled by a simple user interface and no knowledge of simulation or simulation languages is required.

- A user-friendly case study generator facilitates the development of new case studies that suit your business and projects’ nature.

- Use built in models for scheduling, budgeting, resource management and monitoring and control.

- The PTB™ won the PMI project of the year award in 2008.

# MINDVIEW BUSINESS Software

As mentioned in earlier chapters of this text, you can use mind-mapping software to perform a SWOT analysis, create a WBS, and more. After creating a WBS with MindView Business software, you can easily view it in a Gantt chart format as well. Readers of this text can download a 60-day free trial of MindView Business software (vs. the standard 30-day trial) by Matchware, Inc. Go to www.matchware.com/intropm for more information.  Figure B-3 provides sample screen shots from MindView Business.

Figure C-3. MindView Business software (www.matchware.com/intropm)

You can find numerous videos on how to use this powerful software, starting with the Quickstart video on www.matchware.com/intropm. Below is more information taken from www.matchware.com in June, 2013.

Kick-Start Your Planning Sessions!

Need a better way to visualize your tasks and work streams? Frustrated by note taking during planning meetings? Looking for a professional Gantt chart tool that is fast and easy to use? Then MatchWare MindView Business is the ideal project management software tool for you!

MatchWare MindView lets you use Mind Mapping to help every member of your team fully understand the project, contribute to planning, follow the project timeline and clearly visualize all tasks in an organized manner. It lets you take notes “on-the-fly” for criteria or risk management and allows you to attach relevant files to each task in your Mind Map (Excel® files, technical drawings, etc.). Task information such as resources, duration and priorities can also easily be applied directly onto your Mind Map.

MatchWare MindView Business bridges the gap between Mind Mapping and project planning by integrating a dynamic Gantt Chart. This allows you to create most of your project plan in the Mind Map view and then simply switch to the Gantt view for fine-tuning. Your final Gantt chart can then easily be printed or integrated with Microsoft® Project.

# Project Management Certifications

As mentioned in Chapter 1 of this text, many people are interested in certification in project management. I (Kathy Schwalbe) personally earned PMP certification in 1998, before I started writing textbooks, and this book was written to be a resource in earning PMP or CAPM certification as well as a general textbook in healthcare project management.

You can access a pdf file called I wrote called Advice for the Project Management Professional (PMP) Exam and Related Certifications, which describes various certification programs and provides detailed information on PMI’s PMP and CompTIA’s Project+ certifications, the structure and content of these exams, suggestions on preparing for the exams, tips for taking the exams, sample questions, and information on related certifications. This document is an appendix from my other book, Information Technology Project Management, Seventh Edition, and it is provided on my Web sites with publisher permission.

My personal Web site also provides general advice on taking exams and links to free sample PMP exams. Also remember that you do not need work experience to earn the Project + certification or PMI’s Certified Associate in Project Management (CAPM). Consider earning these certifications right after you finish your bachelor’s degree, and consider earning the PMP after you have worked on projects for a few years. You can also earn other certifications from PMI, including the Program Management Professional, Agile Certified Practitioner, Risk Management Professional, and Scheduling Professional. Consult PMI’s Web site for more details.